## Sheet1
PROJECT MANAGEMENTS
Gantt Chart for NPower Website
Tasks | Start Date | Projected Duration (Days) | Actual Duration (Days)
Create Outline for index.html | 2016-02-19 | 7 | 7
Add Multi-Resolution Optimization | 2016-02-21 | 21 | 28
CSS images and colour stylings | 2016-03-02 | 14 | 18
Adding Content to page/place holdings | 2016-03-04 | 7 | 14
JavaScript for Navigation bar | 2016-03-04 | 21 | 21
JavaScript for Banner | 2016-03-14 | 14 | 5
Adding other pages with content | 2016-03-21 | 21
Overall CSS styling | 2016-03-21 | 28
Troubleshooting and Minor Touchups | 2016-04-16 | 21
Group Members: Abdulatif, Arifa, Benjamen, Brian, Vincent